## Testcases
|  |  |  | Date | 03.Nov.22
|  |  |  | Team ID | PNT2022TMID36181
|  |  |  | Project Name | Project – Early detection of chronic kidney disease using machine learning
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite |  | Test Data | Expected Result | Actual Result | Status | Comments | TC for Automation(Y/N) | BUG ID | Executed By
LoginPage_TC_OO1 | Functional | Home Page | Verify user is able to see the when user enter the link in URL | 1. Internet connection 2. Web browser such as Google 3. User know the link 4.Mobile ,Laptop, or System... Needed | 1. Enter URL and click go 2. Click on My Account dropdown button 3. Verify login/Singup popup displayed or not | https://shopenzer.com/ | Login/Signup popup should display | Working as expected | Pass |  | yes |  | manual
LoginPage_TC_OO2 | UI | Home Page | Verify the UI elements in Login/Signup popup | 1. Internet connection 2. Web browser such as Google 3. User know the link 4.Mobile ,Laptop, or System... Needed | 1. Enter URL and click go 2. Click on My Account dropdown button 3. Verify login/Singup popup with below UI elements: a.email text box b.password text box c.Login button d.New customer? Create account link e.Last password? Recovery password link | https://shopenzer.com/ | Application should show below U1 Elements: a. Home b. About c. Contact d. Get started | Working as expected | fail | Steps are not clear to follow | yes | BUG- 1234 | manual
LoginPage_TC_OO3 | Functional | Home Page | Verify user is redirected to the about page, when the user click the "About " button | 1. Internet connection 2. Web browser such as Google 3. User know the link 4.Mobile ,Laptop, or System... Needed | 1. Enter URL(https://shopenzer.com/) and click go 2. Click on My Account dropdown button 3. Enter Valid username/email in Email text box 4. Enter valid password in password text box 5. Click on login button | Click the get started button | User should navigate to user account homepage | Working as expected | Pass |  | yes |  | manual
LoginPage_TC_OO4 | Functional | Login page | Verify user is redirected to chronic website detection page when user click the "Get started" button in the home page. | 1. Internet connection 2. Web browser such as Google 3. User know the link 4.Mobile ,Laptop, or System... Needed | 1. Enter URL(https://shopenzer.com/) and click go 2. Click on My Account dropdown button 3. Enter InValid username/email in Email text box 4. Enter valid password in password text box 5. Click on login button | Click the “check your website”button | Application should show chronic kidney website detection page | Working as expected | Pass |  | yes |  | manual
LoginPage_TC_OO5 | Functional | About page | Verify user is redirected to chronic website detection page when user click the "Get started" button in the home page. | 1. Internet connection 2. Web browser such as Google 3. User know the link 4.Mobile ,Laptop, or System... Needed | 1.Enter URL(https://shopenzer.com/) and click go 2.Click on My Account dropdown button 3.Enter Valid username/email in Email text box 4.Enter Invalid password in password text box 5.Click on login button | Username: chalam@gmail.com password: Testing123678686786876876 | Application should show chronic kidney website detection page |  |  | Here user click the ”check your website” button in about page | yes |  | manual
LoginPage_TC_OO6 | Functional | Chronic kidney detection page | Verify it shows whether the URL entered by the user is safe or unsafe |  | 1.Enter URL(https://shopenzer.com/) and click go 2.Click on My Account dropdown button 3.Enter InValid username/email in Email text box 4.Enter Invalid password in password text box 5. Click on login button | Username: chalam password: Testing123678686786876876 | Application should show 'your safe!!this a legitimate website” |  |  | User enter the URL in correct format | yes |  | Automatic
LoginPage_TC_OO7 | Functional | Chronic kidney detection page | Verify it shows whether the URL entered by the user is safe or unsafe |  |  |  | Application should show 'your safe!!this a legitimate website” | Working as expected | Pass | User enter the URL in correct format | yes |  | Automatic
LoginPage_TC_OO8 | Functional | Chronic kidney detection page | Verify it shows whether the URL entered by the user is safe or unsafe |  |  |  | Application should display” you are on the wrong site. Be cautions!” | Not Working as expected | fail | User enter the URL in correct format | yes |  | Automatic
LoginPage_TC_OO9 | Functional | Chronic kidney detection page | Verify it shows whether the URL entered by the user is safe or unsafe |  |  |  | Application should display “ your safe!! This is a legitimate website” | Not Working as expected | fail | User enter the URL in correct format | yes |  | Automatic

## Testscearnios
Test Scenarios
1 | Verify user is able to see login page
2 | Verify user is able to loginto application or not?
3 | Verify user is able to navigate to create your account page?
4 | Verify user is able to recovery password
5 | Veriify login page elements
Search
1 | Verify user is able to search by entering keywords in search box
2 | Verify user is able to see suggestions based on keyword entered in search box
3 | Verify user is able to see related auto suggestions displaying based on keyword entered in search box
4 | Verify user is able to see no matches found message when no results are matching with entered keyword
5 | Verify user is able to see seach detailed page when nothing entered in textbox